## Daywise-4hourly-execution-plan
Day | Hour 1 (Define & Write) | Hour 2-3 (Build & Experiment) | Hour 4 (Post / Positioning)
Day 1 | RAG basics & failure modes | Build base pipeline skeleton | Intro GenAI positioning
Day 2 | Token limits & KV cache | Implement TokenBudgetService | Token governance post
Day 3 | Why top_k fails | Real embedder + retriever | Top_k misconception post
Day 4 | Why evaluation fails without ground truth | Add similarity scores + expose retrieval scoring | Evaluation pitfalls post
Day 5 | Precision vs recall tradeoff | Add reranking layer (basic) | Reranking improves precision post
Day 6 | Token governance strategies | Enhance TokenBudgetService modes | Token constraints as architecture post
Day 7 | LLM serving fundamentals | Refactor ModelRegistry abstraction | LLM serving vs API call post
Day 8 | Prompting limitations in production | Upgrade PromptBuilder (config-driven) | Prompt engineering myth post
Day 9 | Chunking strategies & tradeoffs | Implement chunking variants (small vs large) | Chunking impact post
Day 10 | Embedding quality vs dimensions | Swap embedding models + compare results | Embedding myths post
Day 11 | Vector DB fundamentals | Integrate FAISS or local index | Vector DB basics post
Day 12 | Latency vs cost tradeoff | Add latency measurement & logging | Latency tradeoff post
Day 13 | Observability in RAG systems | Add logging for retrieval scores & pipeline steps | Observability importance post
Day 14 | Failure mode taxonomy | Tag failure types in pipeline output | RAG failure modes post
Day 15 | Evaluation metrics deep dive | Improve Metrics (embedding-based scoring) | Metrics limitations post
Day 16 | LLM-as-judge evaluation | Add simple LLM judge stub | LLM evaluation post
Day 17 | Ground truth & benchmarking | Add mock evaluation dataset | Benchmarking importance post
Day 18 | Experiment tracking systems | Add experiment logger (runs comparison) | Experiment tracking post
Day 19 | Multi-hop reasoning limitations | Add query expansion (multi-query) | Multi-hop retrieval post
Day 20 | Knowledge graph role in RAG | Add KG-based retrieval stub | KG for RAG post
Day 21 | Hybrid retrieval strategies | Combine keyword + vector retrieval | Hybrid search post
Day 22 | Cost governance in production | Add cost guardrails (limits) | Cost-aware systems post
Day 23 | Throughput & scaling basics | Add batching / parallel calls stub | Scaling challenges post
Day 24 | Caching strategies in RAG | Add response/prefix caching | Caching benefits post
Day 25 | Security & compliance needs | Add audit logging | AI governance post
Day 26 | RBAC & persona control | Extend permission system | RBAC in GenAI post
Day 27 | API design for GenAI systems | Improve FastAPI endpoints | API design post
Day 28 | System integration architecture | Create architecture diagram | End-to-end system post
Day 29 | Tradeoff synthesis & decisions | Compare approaches (k; rerank; chunk) | Decision framework post
Day 30 | Final positioning & showcase | Polish repo + README + examples | Final portfolio post